## Sprint Backlog
PB Name | Task Name | Description and details | Check Out | Status | Remaining Effort [hr]
Menu Browsing & Filtering | Design menu display interface | Create responsive UI components for menu item display with category filtering | Riccardo | Done | 0
Menu Browsing & Filtering | Implement category filtering logic | Develop frontend filtering functionality for menu categories | Leonardo | Done | 0
Menu Browsing & Filtering | Create menu API endpoints | Build REST API for menu item retrieval and category filtering | Giovanni | Done | 0
Menu Browsing & Filtering | Integrate frontend with backend | Connect menu display components with API services | Nicolas | Done | 0
Menu Browsing & Filtering | Add search functionality | Implement text-based search within menu items | Leonardo | Done | 0
Menu Browsing & Filtering | Style menu components | Apply CSS styling and responsive design to menu interface | Giovanni | Done | 0
Menu Item Details | Design item detail modal | Create popup/modal component for detailed menu item information | Nicolas | Done | 0
Menu Item Details | Implement allergen display | Add allergen and nutritional information display functionality | Riccardo | Done | 0
Menu Item Details | Create detailed item API | Build API endpoint for fetching complete menu item details | Giovanni | Done | 0
Menu Item Details | Add image support | Implement menu item image display and management | Nicolas | Done | 0
Order Creation & Management | Design order creation form | Create UI for new order creation with table selection | Riccardo | Done | 0
Order Creation & Management | Implement item addition logic | Develop functionality to add menu items to orders with quantities | Leonardo | Done | 0
Order Creation & Management | Add special instructions field | Create text input for special cooking instructions | Nicolas | Done | 0
Order Creation & Management | Create order API endpoints | Build REST API for order creation and item management | Riccardo | Done | 0
Order Creation & Management | Implement order validation | Add validation logic for order completeness and item availability | Leonardo | Done | 0
Order Creation & Management | Add order summary display | Create order review component before confirmation | Giovanni | Done | 0
Order Filtering & Tracking | Design order status filters | Create UI components for filtering orders by status | Riccardo | Done | 0
Order Filtering & Tracking | Implement table filtering | Add functionality to filter orders by table number | Leonardo | Done | 0
Order Filtering & Tracking | Add timing display | Implement elapsed time and ETA display for orders | Giovanni | Done | 0
Order Filtering & Tracking | Create tracking API | Build API endpoints for order status and timing tracking | Nicolas | Done | 0
Order Filtering & Tracking | Implement real-time updates | Add WebSocket/polling for live order status updates | Leonardo | Done | 0
Order Filtering & Tracking | Style tracking interface | Apply styling to order tracking and filtering components | Giovanni | Done | 0
Menu Item Administration | Design admin interface | Create UI for menu item administration panel | Nicolas | Done | 0
Menu Item Administration | Implement CRUD operations | Develop create, read, update, delete functionality for menu items | Riccardo | Done | 0
Menu Item Administration | Add availability toggle | Create toggle switch for menu item availability status | Giovanni | Done | 0
Menu Item Administration | Create admin API endpoints | Build REST API for menu item administration operations | Nicolas | Done | 0
Menu Item Administration | Implement form validation | Add validation for menu item creation and editing forms | Riccardo | Done | 0
Menu Item Administration | Add bulk operations | Implement bulk edit and delete functionality for menu items | Leonardo | Done | 0
Kitchen Queue Management | Design kitchen display | Create dedicated kitchen interface for order queue | Nicolas | Done | 0
Kitchen Queue Management | Implement chronological sorting | Develop order sorting by creation time and priority | Riccardo | Done | 0
Kitchen Queue Management | Add order details view | Create expandable view for complete order information | Leonardo | Done | 0
Kitchen Queue Management | Create kitchen API | Build API endpoints for kitchen order management | Giovanni | Done | 0
Kitchen Queue Management | Implement auto-refresh | Add automatic refresh functionality for kitchen display | Riccardo | Done | 0
Kitchen Queue Management | Add sound notifications | Implement audio alerts for new orders | Leonardo | Done | 0
Kitchen Status Control | Design status update controls | Create buttons and controls for order status changes | Giovanni | Done | 0
Kitchen Status Control | Implement status transitions | Develop logic for order status progression workflow | Nicolas | Done | 0
Kitchen Status Control | Add preparation filtering | Create filters for orders by preparation stage | Leonardo | Done | 0
Kitchen Status Control | Create status API | Build API endpoints for order status management | Giovanni | Done | 0
Kitchen Status Control | Implement status validation | Add validation for status transition rules | Nicolas | Done | 0
Kitchen Status Control | Add status history | Implement tracking of status change history | Riccardo | Done | 0
Payment Processing | Design payment interface | Create UI for payment processing with method selection | Giovanni | Done | 0
Payment Processing | Implement cash payment | Develop cash payment processing workflow | Nicolas | Done | 0
Payment Processing | Implement card payment | Develop card payment processing integration | Riccardo | Done | 0
Payment Processing | Add payment filtering | Create filters for payment-ready orders by table | Leonardo | Done | 0
Payment Processing | Create payment API | Build API endpoints for payment transaction processing | Nicolas | Done | 0
Payment Processing | Add receipt generation | Implement receipt creation and printing functionality | Riccardo | Done | 0
Payment Summary | Design summary display | Create detailed order breakdown interface | Leonardo | Done | 0
Payment Summary | Implement total calculations | Develop automatic calculation of totals, taxes, and discounts | Giovanni | Done | 0
Payment Summary | Add itemized breakdown | Create detailed list of ordered items with prices | Riccardo | Done | 0
Payment Summary | Create summary API | Build API endpoints for payment summary data | Leonardo | Done | 0
Payment Summary | Implement print functionality | Add printing capability for payment summaries | Giovanni | Done | 0
Payment Summary | Add payment confirmation | Create confirmation dialog and success feedback | Nicolas | Done | 0
Management Analytics | Design analytics dashboard | Create management interface for performance metrics | Leonardo | Done | 0
Management Analytics | Implement real-time statistics | Develop live order count and status statistics | Giovanni | Done | 0
Management Analytics | Add historical data view | Create interface for viewing past order performance | Nicolas | Done | 0
Management Analytics | Create analytics API | Build API endpoints for management data and statistics | Riccardo | Done | 0
Management Analytics | Implement data visualization | Add charts and graphs for performance metrics | Giovanni | Done | 0
Management Analytics | Add export functionality | Create data export features for reporting | Nicolas | Done | 0
System Data Management | Implement auto-refresh | Develop automatic data refresh mechanisms | Riccardo | Done | 0
System Data Management | Add manual refresh controls | Create user-triggered refresh buttons and functionality | Leonardo | Done | 0
System Data Management | Implement data caching | Add intelligent caching for improved performance | Nicolas | Done | 0
System Data Management | Create refresh API | Build API endpoints for data refresh operations | Riccardo | Done | 0
System Data Management | Add refresh indicators | Implement loading states and refresh status indicators | Leonardo | Done | 0
System Data Management | Implement error handling | Add robust error handling for data refresh failures | Giovanni | Done | 0
Role-Based Access | Design role selector | Create interface for switching between user roles | Riccardo | Done | 0
Role-Based Access | Implement role permissions | Develop permission system for different user roles | Leonardo | Done | 0
Role-Based Access | Add role validation | Create validation logic for role-based access control | Giovanni | Done | 0
Role-Based Access | Create authentication API | Build API endpoints for user authentication and authorization | Nicolas | Done | 0
Role-Based Access | Implement session management | Add user session handling and persistence | Leonardo | Done | 0
Role-Based Access | Add role-based UI | Create dynamic UI adaptation based on user role | Giovanni | Done | 0
Database Setup | Design database schema | Create complete database structure for all entities | Nicolas | Done | 0
Database Setup | Implement data models | Develop ORM models for all database entities | Riccardo | Done | 0
Database Setup | Create migration scripts | Build database migration and seeding scripts | Giovanni | Done | 0
Database Setup | Add database indexing | Implement database indexes for performance optimization | Nicolas | Done | 0
Database Setup | Setup database connections | Configure database connection pooling and management | Riccardo | Done | 0
Database Setup | Implement backup strategy | Create automated database backup and recovery procedures | Leonardo | Done | 0
API Gateway Setup | Design API architecture | Plan microservices API structure and endpoints | Nicolas | Done | 0
API Gateway Setup | Implement API gateway | Develop central API gateway for request routing | Riccardo | Done | 0
API Gateway Setup | Add request logging | Implement comprehensive API request and response logging | Leonardo | Done | 0
API Gateway Setup | Setup rate limiting | Add API rate limiting and throttling mechanisms | Giovanni | Done | 0
API Gateway Setup | Implement CORS handling | Configure cross-origin resource sharing policies | Riccardo | Done | 0
API Gateway Setup | Add API documentation | Create comprehensive API documentation and testing interface | Leonardo | Done | 0
Testing & Quality | Write unit tests | Create comprehensive unit test coverage for all components | Giovanni | Done | 0
Testing & Quality | Implement integration tests | Develop integration tests for API and database interactions | Nicolas | Done | 0
Testing & Quality | Add end-to-end tests | Create automated E2E tests for complete user workflows | Leonardo | Done | 0
Testing & Quality | Setup CI/CD pipeline | Implement continuous integration and deployment workflows | Giovanni | Done | 0
Testing & Quality | Add code quality checks | Implement linting, formatting, and code quality standards | Nicolas | Done | 0
Testing & Quality | Performance testing | Conduct load testing and performance optimization | Riccardo | Done | 0
Deployment & DevOps | Setup Docker containers | Create Docker configurations for all services | Giovanni | Done | 0
Deployment & DevOps | Implement container orchestration | Setup Docker Compose for multi-service deployment | Nicolas | Done | 0
Deployment & DevOps | Add monitoring and logging | Implement application monitoring and centralized logging | Riccardo | Done | 0
Deployment & DevOps | Setup production environment | Configure production deployment infrastructure | Leonardo | Done | 0
Deployment & DevOps | Implement health checks | Add service health monitoring and alerting | Nicolas | Done | 0
Deployment & DevOps | Create deployment scripts | Develop automated deployment and rollback procedures | Riccardo | Done | 0
Documentation | Write technical documentation | Create comprehensive technical documentation for developers | Leonardo | Done | 0
Documentation | Create user manuals | Develop user guides for each role in the system | Giovanni | Done | 0
Documentation | Add API documentation | Create detailed API reference documentation | Riccardo | Done | 0
Documentation | Write deployment guide | Create step-by-step deployment and setup instructions | Leonardo | Done | 0
Documentation | Add troubleshooting guide | Create common issues and solutions documentation | Giovanni | Done | 0
Documentation | Create project README | Write comprehensive project overview and getting started guide | Nicolas | Done | 0
1
Note on A1: Feature Name Product Owner: Add the story to the Sprint Backlog Develpment Team: Assign tasks for completion
Note on B1: Development Team: Add a short task name
Note on C1: Development Team: Describe the activity and add comments as needed. Add new lines on the same cell with [alt+enter]
Note on D1: Development Team: Select your name if you are working on it, remove it if you are not working on it anymore so anyone else can pull the activity.
Note on E1: Development Team: Select current status
Note on F1: Development Team: Fill the estimated remaining effort (how many horus of work are left to complete the task)

## Burndown Chart
Date | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04
Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Real | 26 | 24 | 20 | 20 | 20 | 16 | 12 | 5 | 1 | 1 | 1 | 1 | 1 | 0
Plan | 26 | 24 | 22 | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
0 | Remaining Effort [hr]
13 | Number of days in sprint
Reference: Scrum in a Nutshell
Reference: Understanding Burndown Charts
Note on A2: Sprint Date At the beginning of the sprint Scrum Master: Assign the dates for the current Sprint
Note on A3: Sprint Day At the beginning of the Sprint Scrum Master: Write the day number
Note on A4: Remaining effort for the respective date. Scrum Master: Fill manually each sprint day with the remaining effort data.
Note on M4: Scrum Master: Copy this value to the row Real on today's column. with [ctrl+shit+v]
Note on A5: Ideal plan to finish on time At the begining of the sprint Scrum Master: Drag formula as needed to fill the Sprint
Note on A7: Scrum Master: Copy this value to the row Real on today's column. with [ctrl+shit+v]

## Product Backlog
Story Name | Story Description | Status
Menu Browsing & Filtering | View and filter restaurant menu items by category (appetizers, main dishes, desserts, beverages, side dishes) with descriptions and prices | Done
Menu Item Details | Display detailed information about menu items including allergens and nutritional information | Done
Order Creation & Management | Create new orders for specific tables and add menu items with quantities and special cooking instructions | Done
Order Filtering & Tracking | Filter orders by status and table number with elapsed time and estimated completion tracking | Done
Menu Item Administration | Add, modify, delete menu items and toggle availability status with complete details and pricing | Done
Kitchen Queue Management | Display incoming orders in chronological order with preparation status updates and order details | Done
Kitchen Status Control | Mark orders as "preparing" and "ready" status with filtering by preparation stage on kitchen display | Done
Payment Processing | Process cash and card payments for ready orders with filtering by table number | Done
Payment Summary | Display detailed order breakdown with total amounts for payment verification | Done
Management Analytics | View real-time order statistics, counts, and historical order data for performance analysis | Done
System Data Management | Enable automatic and manual refresh of order and menu data for real-time updates | Done
Role-Based Access | Access and switch between all system roles (customer, waiter, chef, cashier, manager) for operational oversight | Done
Note on A1: Product Owner: Write the name of the story, drag rows according to priorities
Note on B1: Product Owner: Write a detailed description of the story. Be specific about high priority features Make new lines in the same cell with [alt+enter]
Note on C1: Product Owner: Select current status

## Change Log
Version | Date | Changes | Author
v0.1.0 | 2025-10-05 | Project initiation and repository setup | Nicolas
v0.2.0 | 2025-10-23 | Core microservices architecture implementation and API Gateway setup | Riccardo
v0.2.1 | 2025-10-24 | Docker-compose configuration fixes and deployment optimization | Nicolas
v0.3.0 | 2025-10-24 | Backend service refactoring to Flask framework and project rebranding | Nicolas
v1.0.0 | 2025-10-24 | Release 1.0: Frontend MVP - React application with core UI components | Nicolas
v1.1.0 | 2025-10-27 | Menu management system with real-time updates | Riccardo
v1.1.1 | 2025-10-27 | Real-time update implementation | Riccardo
v1.2.0 | 2025-10-27 | Order management system and billing workflow implementation | Riccardo
v1.2.1 | 2025-10-27 | Docker fix for optimal fit with Node's services in frontend | Nicolas
v1.3.0 | 2025-10-28 | API-gateway implementation and Docker integration | Giovanni
v1.3.1 | 2025-10-28 | Menu-inventory implementation and Docker integration | Giovanni
v1.3.2 | 2025-10-28 | Order-management implementation and Docker integration | Giovanni
v1.4.0 | 2025-10-29 | UX/UI design and dashboard functionality implementation | Nicolas
v1.4.1 | 2025-10-29 | Role-based access control and authentication system | Giovanni
v1.4.2 | 2025-10-29 | Roles update | Giovanni
v2.0.0 | 2025-10-29 | Release 2.0: Complete implementation and README final update | Nicolas
v2.1.0 | 2025-10-30 | Mock-up added | Leonardo
v2.2.0 | 2025-10-30 | Added test folder | Leonardo
v2.3.0 | 2025-10-30 | Added DataMetrics.json | Leonardo
v2.4.0 | 2025-11-04 | Final patch and minor fixes | Nicolas

## Setup
Product Backlog Status Options | Spring Backlog Status Options | Development Team
Not To Do | To Do | Riccardo
To Do | Doing | Leonardo
Done | Done | Giovanni
| OK | Nicolas